UNIT-2 AGILE MINI-PROJECT

Enterprise Student Record and Academic Management Platform
Agile Product Development Based on Unit 1

Submitted by: Bhairavi Santosh Bhambare

PRN: 2125UDSF1019

# 1. Agile Project Planning Report

This mini-project applies Agile planning practices to the Student Record and Academic Management Platform. The project is organized around product vision, Scrum roles, epics, user stories, acceptance criteria, backlog prioritization, story-point estimation, sprint planning, Scrum tracking, reviews, retrospectives, and Agile framework comparison.

This document therefore represents the Agile product-development phase of the same project rather than a separate project.

Unit 1 focused on understanding the business problem, users, requirements, product vision, MVP, roadmap, and system architecture. Unit 2 translates that foundation into Agile product-development artifacts: Scrum roles, epics, user stories, acceptance criteria, a prioritized product backlog, story-point estimates, sprint planning, Scrum tracking, reviews, retrospectives, and an Agile framework comparison.

This Unit 2 Agile Mini-Project continues the Enterprise Student Record and Academic Management Platform developed in Unit 1. The product vision, requirements, MVP, architecture, and roadmap established in Unit 1 provide the foundation for Agile planning in Unit 2.

# Unit 1 to Unit 2 Continuity

# 2. Business Problem and Product Vision

The business problem identified in Unit 1 is carried forward into Agile planning: educational institutions need an organized way to manage student records, attendance, academic performance, course registration, and reporting. The proposed platform addresses these needs through a scalable web-based application.

Product Vision: Develop a secure and user-friendly Enterprise Student Record and Academic Management Platform that enables educational institutions to efficiently manage student records, attendance, academic performance, course registration, and reporting through a scalable web-based application.

# 3. Scrum Team Structure

| Role | Team Member | Main Responsibility |
| --- | --- | --- |
| Product Owner | To be assigned | Define requirements, prioritize backlog, represent stakeholders, accept completed work. |
| Scrum Master | To be assigned | Facilitate Scrum ceremonies, remove impediments, support Agile practices. |
| Development Team | Student project team | Design, code, test, document, and demonstrate software features. |

Note: The Scrum roles are defined for the Agile project structure. Team-member names are intentionally left unassigned because no specific team composition was provided for this assignment.

# 4. Scrum Roles and Responsibilities

Product Owner: Defines product requirements, prioritizes the Product Backlog, represents stakeholder interests, and accepts completed work.

Scrum Master: Facilitates Scrum ceremonies, removes project impediments, ensures Agile practices are followed, and supports collaboration.

Development Team: Designs the application, writes code, tests software, prepares documentation, and demonstrates completed features.

# 5. Project Epics

| Epic | Scope / Features |
| --- | --- |
| Epic 1 – Student Management | Student Registration; Student Profile Management; Student Search; Student Update; Student Deletion |
| Epic 2 – Course Management | Add Course; Update Course; Assign Students; View Course Details |
| Epic 3 – Attendance Management | Record Attendance; View Attendance; Attendance Reports |
| Epic 4 – Marks and Academic Performance | Enter Marks; Update Marks; Calculate Grades; Generate Result Sheets |
| Epic 5 – Authentication and Security | User Login; Logout; Password Reset; Role-Based Access Control |
| Epic 6 – Notifications | Attendance Alerts; Examination Notifications; Result Notifications |
| Epic 7 – Reporting | Student Reports; Attendance Reports; Performance Reports; Course Reports |

# 6. User Story Repository

| ID | Epic | User Story | Points |
| --- | --- | --- | --- |
| US-01 | Authentication | As a registered user, I want to log in so that I can securely access the platform. | 5 |
| US-02 | Authentication | As a user, I want to log out so that my session is securely ended. | 2 |
| US-03 | Student Management | As an administrator, I want to add a student so that the student's record is stored. | 5 |
| US-04 | Student Management | As a faculty member, I want to search for a student so that I can quickly find the required record. | 3 |
| US-05 | Student Management | As an administrator, I want to update student details so that records remain accurate. | 3 |
| US-06 | Student Management | As an administrator, I want to delete a student record so that obsolete records can be removed. | 3 |
| US-07 | Course Management | As an administrator, I want to add a course so that students can be assigned to it. | 5 |
| US-08 | Course Management | As an administrator, I want to assign students to courses so that enrollment is maintained. | 5 |
| US-09 | Attendance | As a faculty member, I want to record attendance so that attendance records remain accurate and updated. | 5 |
| US-10 | Attendance | As a faculty member, I want to view attendance so that I can monitor student participation. | 3 |
| US-11 | Marks | As a faculty member, I want to enter marks so that academic performance is recorded. | 5 |
| US-12 | Marks | As the system, I want to calculate grades so that results can be generated consistently. | 5 |
| US-13 | Notifications | As a student, I want to receive attendance alerts so that I am informed about my attendance status. | 3 |
| US-14 | Reporting | As an administrator, I want to generate student reports so that academic information can be reviewed. | 5 |
| US-15 | Reporting | As a faculty member, I want to generate attendance reports so that attendance can be analyzed. | 5 |

# 7. Acceptance Criteria

| User Story | Acceptance Criteria |
| --- | --- |
| US-01 Login | Login page loads; registered users can log in; invalid credentials show an error; successful login redirects to dashboard; session management works correctly. |
| US-03 Add Student | Student form loads; required details can be entered; valid data is saved; duplicate/invalid data is handled; saved student can be searched. |
| US-04 Search Student | Search accepts relevant student details; matching records are displayed; no-match results are handled clearly. |
| US-07 Add Course | Authorized user can add a course; required fields are validated; course is saved; course appears in course listing. |
| US-09 Record Attendance | Faculty can select a course; select a lecture date; mark attendance; attendance is saved successfully; attendance can be reported. |
| US-11 Enter Marks | Faculty can select a student/course; marks can be entered; invalid values are rejected; valid marks are saved. |
| US-12 Calculate Grades | System uses defined grading rules; grade is calculated correctly; result is associated with the correct student/course. |
| US-14 Student Reports | Authorized user can select report criteria; report is generated; report contains correct student information. |

# 8. Prioritized Product Backlog

| Rank | Priority | User Story | Points |
| --- | --- | --- | --- |
| 1 | High | US-01 Login | 5 |
| 2 | High | US-03 Add Student | 5 |
| 3 | High | US-04 Search Student | 3 |
| 4 | High | US-09 Record Attendance | 5 |
| 5 | High | US-05 Update Student | 3 |
| 6 | Medium | US-07 Add Course | 5 |
| 7 | Medium | US-08 Assign Students | 5 |
| 8 | Medium | US-10 View Attendance | 3 |
| 9 | Medium | US-14 Student Reports | 5 |
| 10 | Medium | US-13 Attendance Alerts | 3 |
| 11 | Low | US-11 Enter Marks | 5 |
| 12 | Low | US-12 Calculate Grades | 5 |
| 13 | Low | US-02 Logout | 2 |
| 14 | Low | US-06 Delete Student | 3 |
| 15 | Low | US-15 Attendance Reports | 5 |

# 9. Story Point Estimation

| Story Points | Complexity |
| --- | --- |
| 1 | Very Easy |
| 2 | Easy |
| 3 | Moderate |
| 5 | Difficult |
| 8 | Very Difficult |
| 13 | Highly Complex |

Planning Poker can be used by the team to collaboratively estimate the effort of each User Story.

# 10. Sprint Planning

| Sprint | Goal | Activities |
| --- | --- | --- |
| Sprint 1 | User authentication and project setup | Repository initialization; User registration; Login; Basic UI; Testing |
| Sprint 2 | Student Management Module | Add Student; Search Student; Update Student; Delete Student |
| Sprint 3 | Course and Attendance Management | Add Course; Assign Courses; Record Attendance; Attendance Reports |
| Sprint 4 | Academic Performance and Reporting | Enter Marks; Update Marks; Calculate Grades; Result Sheets; Reports; Notifications |

# 11. Sprint Backlog

| Sprint | Selected Stories / Tasks |
| --- | --- |
| Sprint 1 | US-01 Login; US-02 Logout; repository setup; basic UI; authentication testing |
| Sprint 2 | US-03 Add Student; US-04 Search Student; US-05 Update Student; US-06 Delete Student |
| Sprint 3 | US-07 Add Course; US-08 Assign Students; US-09 Record Attendance; US-10 View Attendance |
| Sprint 4 | US-11 Enter Marks; US-12 Calculate Grades; US-13 Attendance Alerts; US-14 Student Reports |

# 12. Scrum Board

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Login | Add Student | Search Student | Reports | Project Setup |
| Course | Attendance | Notifications |  |  |
| Marks | Student Update | Course Assignment |  |  |

# 13. Planned / Simulated Burndown Chart

For this mini-project, the burndown data below is a simulated planning example. In an actual implementation, completed and remaining story points would be updated from the team's real sprint progress.

| Sprint | Starting Points | Completed Points | Remaining Points |
| --- | --- | --- | --- |
| Sprint 1 | 12 | 10 | 2 |
| Sprint 2 | 16 | 13 | 3 |
| Sprint 3 | 18 | 15 | 3 |
| Sprint 4 | 18 | 18 | 0 |

# 14. Sprint Review Report

During the Sprint Review, the team demonstrates the completed features to stakeholders, collects feedback, and identifies changes or additional requirements. The Product Owner confirms whether the completed stories satisfy their acceptance criteria.

# 15. Sprint Retrospective Report

| Area | Observation | Improvement Action |
| --- | --- | --- |
| What went well | Team collaboration and incremental delivery | Continue regular communication |
| Challenges | Requirement clarification and task dependencies | Clarify acceptance criteria before sprint start |
| Improvement | Better progress tracking needed | Update Scrum Board and burndown regularly |

# 16. Agile Framework Comparison

| Framework | Key Idea | Suitability for This Project |
| --- | --- | --- |
| Scrum | Time-boxed sprints, roles, ceremonies, backlog | Highly suitable for a student team and incremental delivery |
| Kanban | Visual workflow and continuous flow | Useful for tracking tasks and limiting work in progress |
| Extreme Programming (XP) | Engineering practices and frequent feedback | Useful where strong testing and coding practices are required |
| Lean Development | Reduce waste and maximize value | Useful for efficient project delivery |
| LeSS | Scaling Scrum to multiple teams | More suitable for larger Scrum environments |
| SAFe | Scaled Agile practices for larger organizations | More complex than required for this mini-project |
| Scrum@Scale | Scaling Scrum across teams | Useful when several Scrum teams must coordinate |

Recommended framework: Scrum, because the assignment itself is structured around Scrum roles, product backlog, sprints, Scrum Board, Sprint Review, and Sprint Retrospective.

# 17. Project Timeline and Release Roadmap

| Phase | Major Deliverables | Expected Outcome |
| --- | --- | --- |
| Phase 1 | Vision, roles, epics | Project scope and responsibilities defined |
| Phase 2 | User stories, acceptance criteria, backlog | Prioritized requirements prepared |
| Phase 3 | Sprint 1 – Authentication | Project setup and secure login foundation |
| Phase 4 | Sprint 2 – Student Management | Student records can be managed |
| Phase 5 | Sprint 3 – Course & Attendance | Courses and attendance can be managed |
| Phase 6 | Sprint 4 – Marks, Reports & Notifications | Academic reporting and supporting features |
| Final | Review, retrospective, documentation | Complete Agile project submission |

Unit 2 Completion Statement: The Agile artifacts in this document convert the Unit 1 product foundation into an actionable Scrum-based delivery plan. The backlog, stories, estimates, and sprints are planning artifacts for the mini-project; they do not imply that the software has already been implemented or that a formal external team has been created.

# 18. Conclusion

The Student Record and Academic Management Platform can be developed incrementally using Agile practices. The project divides the product into manageable epics and user stories, prioritizes work through a Product Backlog, estimates effort using Story Points, and delivers functionality through multiple Sprints. Scrum provides a practical framework for collaboration, progress tracking, review, and continuous improvement.

# 19. Submission Checklist

Agile Project Planning Report

Product Vision Document

Scrum Team Structure

Scrum Roles and Responsibilities Document

Epic Documentation

User Story Repository

Acceptance Criteria Document

Prioritized Product Backlog

Story Point Estimation Sheet

Sprint Planning Document

Sprint Backlog

Scrum Board

Burndown Chart

Sprint Review Report

Sprint Retrospective Report

Agile Framework Comparison Report

Project Timeline and Release Roadmap

Complete Agile Documentation